## Sheet1
Project Phase | Description | Start date | Completion date
Design / Requirements Refinement
| Develop Functional Design Document with vendor | 2026-09-01 | 2026-12-18
| Stage Gate: SteerCo signs off on Design | 2027-01-12 | 2027-01-22
Development / Configuration
| Development Build Begins | 2027-01-25 | 2027-01-25
| Dev Complete | 2027-06-07 | 2027-06-07
Testing
| Stage Gate: Testing Sign-Off | 2027-09-13 | 2027-09-17
Training
| Develop Training Materials & User Guides | 2027-06-02 | 2027-07-18
Pilot Go-Live (Pilot Office)
| Pilot Office Go-Live | 2027-10-01 | 2027-10-01
Broader Deployment (Remaining Offices)
| Stage Gate: Broader Deployment Go / No-Go | 2028-03-16 | 2028-03-16