|  | ## Title: Feasibility Assessment for Mental Health Agency Licensure and Billing ## Organization: International Rescue Committee |
| --- | --- |

- BACKGROUND

The International Rescue Committee, Inc. (IRC) is considering whether to pursue licensure as a mental health care agency capable of billing for outpatient clinical services in the United States. This would represent a significant institutional decision with implications for regulatory compliance, financial sustainability, systems and infrastructure, staffing models, governance, and organizational risk.

The IRC is seeking a qualified consultant or firm to conduct a decision-grade feasibility assessment to equip executive leadership with the information required to determine whether IRC should proceed with further exploration. We seek a qualified consultant or firm with expertise in behavioral health operations, reimbursement models, and regulatory compliance to conduct this feasibility assessment in relation to four states – California, Arizona, Georgia and Idaho.

- GOALS

The goal of this engagement is to understand the financial, operational, and regulatory implications of IRC becoming a mental health agency capable of billing for behavioral health services. A feasibility assessment is required to provide leadership with an evidence-based analysis of:

- Regulatory feasibility: High-level licensure pathways, Medicaid and other payer participation requirements, and compliance considerations

- Financial viability: Order-of-magnitude start-up and ongoing costs, revenue potential, breakeven considerations, and financial risk

- Operational readiness: Implications for systems (IT, billing, compliance), staffing models, clinical oversight, and governance

- Risk exposure: Organizational, clinical, compliance, financial, and reputational risks associated with billable care

- Strategic options: Comparison of potential approaches, including pilot vs. scale, partnership vs. standalone models, and telehealth-enabled strategies

- Implementation timeline: Milestones from agency formation to first billable service

- Client population viability: Demand, service gaps, and eligibility considerations for IRC’s target population (for purposes of this assessment, we are looking at people from immigrant and refugee backgrounds

The assessment should culminate in a clear recommendation regarding whether IRC should proceed to a next phase of licensure exploration, defer, or decline pursuit at this time.

- Scope of Work and Tasks

The consultant will perform, at minimum, the following tasks:

- Discovery and Organizational Context

  - Review of IRC’s mission, service model, current organizational structure, and relevant internal capabilities

  - Conduct interviews with key stakeholders to understand strategic objectives, constraints, and risk tolerance

- Regulatory Feasibility Analysis

  - Summarize federal requirements applicable to licensed mental health agencies, including high-level HIPAA considerations

  - Conduct state-specific regulatory feasibility analyses for Georgia, California, Idaho, and Arizona, including:

    - Agency licensure pathways

    - Medicaid enrollment and payer participation considerations

    - Core compliance obligations and oversight requirements

  - Identify major regulatory risks, dependencies, and barriers to entry

- Financial Viability Assessment

  - Develop high-level estimates of start-up and ongoing costs associated with licensure and billable care (e.g., staffing, compliance, systems, oversight)

  - Provide indicative reimbursement ranges by payer type (e.g., Medicaid, Medicare, commercial insurance), inclusive of interpretation services where applicable

  - Assess time-to-first-billable-service considerations and breakeven dynamics

  - Identify key financial assumptions, sensitivities, and areas of uncertainty relevant to leadership decision-making

- Market and Population Considerations

  - Assess the potential client pool given IRC’s focus on refugees and immigrants, including language access needs

  - Identify known gaps in behavioral health services for this population and relevant eligibility considerations

- Operational Readiness and Governance Implications

  - Assess implications for systems (billing, compliance, data, IT), staffing models, clinical supervision, and quality assurance

  - Identify governance, oversight, and accountability considerations associated with clinical service delivery

  - Evaluate organizational readiness and capacity gaps

- Organizational Risk Assessment

  - Identify material organizational, clinical, compliance, financial, and reputational risks associated with becoming a billable mental health provider

  - Highlight risk mitigation considerations and residual risk exposure

- Strategic Options Analysis

  - Evaluate and compare potential pathways, including:

    - Limited pilot in one or more states

    - Multi-state telehealth-enabled model

    - Partnership or subcontracting with existing licensed providers

    - Standalone licensure model

  - For each option, assess relative feasibility, scalability, risk, and organizational burden

- Recommendations and Decision Support

  - Synthesize findings into a clear, evidence-based recommendation regarding whether IRC should proceed with further exploration of licensure

  - Clearly articulate conditions under which proceeding may or may not be advisable

- Deliverables

- Comprehensive Feasibility Report - A written report addressing all scope areas, including supporting analysis, assumptions, and findings.

- Executive Summary - A concise, leadership-level summary suitable for executive and board review.

- Go / No-Go Recommendation Memo - A focused, decision-oriented memo outlining the recommended path forward, with clear rationale across regulatory, financial, operational, and risk dimensions.

- Consultant Qualifications

Proposers should demonstrate:

- Expertise in healthcare management, behavioral health operations, or health policy.

- Experience with Medicaid/Medicare and commercial payer reimbursement processes.

- Knowledge of state and federal mental health licensing and telehealth regulations.

- Strong analytical, financial modeling, and communication skills.

- Proposal Requirements

Proposals should include:

- Overview of consultant/consultant agency and relevant experience

- Proposed approach and methodology

- Detailed project timeline

- Budget and fee structure

- References from similar projects

- Evaluation Criteria

Proposals will be evaluated based on the following weighted criteria:

- Relevant Experience and Qualifications – 25%

- Proposed Methodology and Work Plan – 50%

- Cost Proposal – 25%

Quotes to be received by April 21st.

All quotations and questions should be sent to Taylor.Foltz@rescue.org and Elizabeth.Farmer@rescue.org.